## KPI Summary
Row Labels | Count of KPI
Agile Delivery KPIs | 12
Communication Management | 10
Cost Management | 15
Financial Forecasting | 10
Governance & Decision Management | 12
Lessons Learned & Continuous Improvement | 8
Procurement & Contract Management | 10
Project Closure & Transition | 10
Quality Management | 15
Resource Management | 12
Risk & Issue Management | 15
Schedule Management | 15
Scope Management | 12
Stakeholder Management | 10
(blank)
Grand Total | 166

## KPI Repository
KPI ID | Control Domain | KPI | Definition / Description | Formula / Calculation | Nature | Activation | When to Use | Trigger | Decision | Owner | Data Source | Cadence | Target / Tolerance | Direction of Improvement | What the KPI Indicates | Action | Illustrative Example | Sample Value | Source Slide
KPI-001 | Schedule Management | Schedule Variance (SV) | Measures whether work is ahead of or behind the approved schedule. | EV − PV | Lagging / performance | Trigger-based | Planning through execution; use in weekly delivery and forecast reviews | Trigger on material adverse trend, exception, or management concern | Is the schedule management variance within the approved tolerance, and what corrective action is required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | Context-dependent | ↔ Context-dependent / target-driven | Measures whether work is ahead of or behind the approved schedule. The preferred result is to remain close to the approved target or tolerance. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | EV ₹8.5Cr; PV ₹9Cr | −₹0.5Cr | 4
KPI-002 | Schedule Management | Schedule Performance Index (SPI) | Measures schedule efficiency against the baseline. | EV ÷ PV | Lagging / performance | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: ≥ 1.00 | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | ≥ 1.00 | ↑ Higher is better | Measures schedule efficiency against the baseline. An increase generally indicates stronger performance or control. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | EV 8.5; PV 9.0 | 0.94 | 4
KPI-003 | Schedule Management | Milestone Achievement % | Percentage of planned milestones achieved by their baseline dates. | [Milestones achieved on time ÷ planned milestones] × 100 | Lagging / outcome | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: ≥ 95% | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | ≥ 95% | ↑ Higher is better | Percentage of planned milestones achieved by their baseline dates. An increase generally indicates stronger performance or control. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | 46 of 48 milestones on time | 95.8% | 4
KPI-004 | Schedule Management | Critical Path Health | Percentage of critical-path activities remaining on track. | [Critical activities on track ÷ total critical activities] × 100 | Lagging / performance | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: ≥ 90% | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | ≥ 90% | ↑ Higher is better | Percentage of critical-path activities remaining on track. An increase generally indicates stronger performance or control. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | 27 of 30 critical tasks on track | 90% | 4
KPI-005 | Schedule Management | Milestone Slippage % | Percentage of milestones delayed beyond their baseline dates. | [Delayed milestones ÷ planned milestones] × 100 | Lagging / performance | Trigger-based | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: ≤ 5% | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | ≤ 5% | ↓ Lower is better | Percentage of milestones delayed beyond their baseline dates. A decline generally indicates improving control or less exposure. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | 2 of 48 milestones late | 4.2% | 4
KPI-006 | Schedule Management | Planned vs Actual Completion | Compares planned completion with actual completion. | Actual % complete − planned % complete | Lagging / outcome | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Trigger on material adverse trend, exception, or management concern | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | Context-dependent | ↑ Higher is better | Compares planned completion with actual completion. An increase generally indicates stronger performance or control. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | Actual 72%; plan 75% | −3 pp | 4
KPI-007 | Schedule Management | Sprint Predictability | Measures how reliably a sprint team delivers its committed scope. | [Completed committed work ÷ committed work] × 100 | Lagging / performance | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: ≥ 85% | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | ≥ 85% | ↑ Higher is better | Measures how reliably a sprint team delivers its committed scope. An increase generally indicates stronger performance or control. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | 34 of 40 committed points | 85% | 4
KPI-008 | Schedule Management | Lead Time | Elapsed time from request or approval to delivery. | Delivery date − request date | Leading | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: Lower is better | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | Lower is better | ↓ Lower is better | Elapsed time from request or approval to delivery. A decline generally indicates improving control or less exposure. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | Request: 1 Jun; delivery: 10 Jun | 9 days | 4
KPI-009 | Schedule Management | Cycle Time | Elapsed time required to complete an activity or work item. | Completion date − start date | Leading | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: Lower is better | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | Lower is better | ↓ Lower is better | Elapsed time required to complete an activity or work item. A decline generally indicates improving control or less exposure. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | Start: 4 Jun; complete: 8 Jun | 4 days | 4
KPI-010 | Schedule Management | Activity Completion % | Percentage of scheduled activities completed. | [Completed activities ÷ planned activities] × 100 | Lagging / outcome | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: ≥ 95% | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | ≥ 95% | ↑ Higher is better | Percentage of scheduled activities completed. An increase generally indicates stronger performance or control. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | 190 of 200 activities complete | 95% | 4
KPI-011 | Schedule Management | Schedule Adherence % | Measures execution against scheduled dates. | [Activities completed on schedule ÷ activities completed] × 100 | Lagging / performance | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: ≥ 90% | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | ≥ 90% | ↑ Higher is better | Measures execution against scheduled dates. An increase generally indicates stronger performance or control. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | 180 of 200 activities on time | 90%
KPI-012 | Schedule Management | Float / Slack | Measures schedule flexibility available before an activity affects the finish date. | Late start − early start | Leading | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: Positive / protected | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | Positive / protected | ↑ Higher / positive is better | Measures schedule flexibility available before an activity affects the finish date. An increase generally indicates stronger performance or control. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | Critical activity has 2 days buffer | 2 days | 4
KPI-013 | Schedule Management | Replan Frequency | Measures how often the approved schedule is materially re-baselined. | Number of approved replans per period | Leading | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: As low as practical | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | As low as practical | ↔ Context-dependent / target-driven | Measures how often the approved schedule is materially re-baselined. The preferred result is to remain close to the approved target or tolerance. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | 2 approved replans in 6 months | 0.33/month | 4
KPI-014 | Schedule Management | Baseline Stability Index | Measures how stable the approved schedule baseline remains. | 1 − [approved baseline changes ÷ baseline elements] | Lagging / performance | Always-on | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: ≥ 90% | Are we on schedule, and where is schedule intervention required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | ≥ 90% | ↑ Higher is better | Measures how stable the approved schedule baseline remains. An increase generally indicates stronger performance or control. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | 5 baseline changes across 120 items | 95.8% | 4
KPI-015 | Schedule Management | Forecast vs Plan Variance | Measures forecast completion deviation from the approved plan. | Forecast finish − baseline finish | Leading | Trigger-based | Planning through execution; use in weekly delivery and forecast reviews | Threshold/tolerance: ≤ agreed tolerance | Is the schedule management variance within the approved tolerance, and what corrective action is required? | Project Manager / PMO | Integrated project schedule / baseline / scheduling tool | W | ≤ agreed tolerance | ↓ Lower is better | Measures forecast completion deviation from the approved plan. A decline generally indicates improving control or less exposure. | Reforecast critical activities, recover slippage, protect the critical path, or approve a controlled replan. | Forecast 30 Sep; baseline 25 Sep | +5 days | 4
KPI-016 | Cost Management | Budget Variance | Difference between approved budget and actual cost. | Budget − Actual Cost | Lagging / performance | Trigger-based | Planning through execution; use in weekly cost-control and forecast reviews | Threshold/tolerance: ≥ 0 | Is the cost management variance within the approved tolerance, and what corrective action is required? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | ≥ 0 | ↑ Higher is better | Difference between approved budget and actual cost. An increase generally indicates stronger performance or control. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | Budget ₹10Cr; actual ₹9.6Cr | +₹0.4Cr | 5
KPI-017 | Cost Management | Cost Performance Index (CPI) | Measures cost efficiency of work performed. | EV ÷ AC | Lagging / performance | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Threshold/tolerance: ≥ 1.00 | Are we within cost plan, and is corrective action needed to protect the budget? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | ≥ 1.00 | ↑ Higher is better | Measures cost efficiency of work performed. An increase generally indicates stronger performance or control. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | EV ₹9Cr; AC ₹9.6Cr | 0.94 | 5
KPI-018 | Cost Management | Earned Value (EV) | Budgeted value of work actually completed. | % complete × total budget | Lagging / performance | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Trigger on material adverse trend, exception, or management concern | Are we within cost plan, and is corrective action needed to protect the budget? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | Context-dependent | ↔ Context-dependent / target-driven | Budgeted value of work actually completed. The preferred result is to remain close to the approved target or tolerance. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | 90% of ₹10Cr budget earned | ₹9Cr | 5
KPI-019 | Cost Management | Planned Value (PV) | Budgeted value of work planned to be completed. | Baseline budget × planned % complete | Lagging / performance | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Trigger on material adverse trend, exception, or management concern | Are we within cost plan, and is corrective action needed to protect the budget? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | Context-dependent | ↔ Context-dependent / target-driven | Budgeted value of work planned to be completed. The preferred result is to remain close to the approved target or tolerance. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | 90% planned of ₹10Cr | ₹9Cr | 5
KPI-020 | Cost Management | Actual Cost (AC) | Actual expenditure incurred for completed work. | Sum of actual project costs | Lagging / performance | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Trigger on material adverse trend, exception, or management concern | Are we within cost plan, and is corrective action needed to protect the budget? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | Context-dependent | ↔ Context-dependent / target-driven | Actual expenditure incurred for completed work. The preferred result is to remain close to the approved target or tolerance. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | Invoices + payroll + vendors | ₹9.6Cr | 5
KPI-021 | Cost Management | Estimate to Complete (ETC) | Forecast of additional cost required to finish the project. | EAC − AC | Lagging / performance | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Trigger on material adverse trend, exception, or management concern | What is the latest expected outcome, and is corrective action needed now? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | Context-dependent | ↔ Context-dependent / target-driven | Forecast of additional cost required to finish the project. The preferred result is to remain close to the approved target or tolerance. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | EAC ₹10.2Cr; AC ₹9.6Cr | ₹0.6Cr | 5
KPI-022 | Cost Management | Estimate at Completion (EAC) | Forecast of total final project cost. | AC + [BAC − EV] ÷ CPI | Lagging / outcome | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Trigger on material adverse trend, exception, or management concern | What is the latest expected outcome, and is corrective action needed now? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | Context-dependent | ↑ Higher is better | Forecast of total final project cost. An increase generally indicates stronger performance or control. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | AC ₹9.6Cr; BAC ₹10Cr; CPI 0.94 | ₹10.0Cr | 5
KPI-023 | Cost Management | Cost Burn Rate | Average cost incurred over a defined period. | Total cost incurred ÷ elapsed project periods | Leading | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Trigger on material adverse trend, exception, or management concern | Are we within cost plan, and is corrective action needed to protect the budget? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | Context-dependent | ↓ Lower is better | Average cost incurred over a defined period. A decline generally indicates improving control or less exposure. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | ₹9.6Cr over 12 months | ₹0.8Cr/month | 5
KPI-024 | Cost Management | Monthly Spend | Actual project expenditure incurred in the month. | Sum of monthly project costs | Lagging / performance | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Trigger on material adverse trend, exception, or management concern | Are we within cost plan, and is corrective action needed to protect the budget? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | Context-dependent | ↔ Context-dependent / target-driven | Actual project expenditure incurred in the month. The preferred result is to remain close to the approved target or tolerance. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | April project spend | ₹0.75Cr | 5
KPI-025 | Cost Management | Resource Cost Utilization | Measures how efficiently budgeted resource cost is being used. | Actual resource cost ÷ planned resource cost × 100 | Leading | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Trigger on material adverse trend, exception, or management concern | Do we have the right capacity and allocation to sustain delivery? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | Context-dependent | ↑ Higher is better | Measures how efficiently budgeted resource cost is being used. An increase generally indicates stronger performance or control. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | Actual ₹3.8Cr; plan ₹4Cr | 95% | 5
KPI-026 | Cost Management | Cost Forecast Accuracy | Measures accuracy of the project cost forecast. | 1 − [Forecast − Actual] ÷ Actual | Leading | Trigger-based | Planning through execution; use in weekly cost-control and forecast reviews | Threshold/tolerance: ≥ 90% | What is the latest expected outcome, and is corrective action needed now? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | ≥ 90% | ↑ Higher is better | Measures accuracy of the project cost forecast. An increase generally indicates stronger performance or control. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | Forecast ₹10.1Cr; actual ₹10Cr | 99% | 5
KPI-027 | Cost Management | Cost Variance % | Relative difference between planned and actual cost. | [Actual Cost − Planned Cost] ÷ Planned Cost × 100 | Lagging / performance | Trigger-based | Planning through execution; use in weekly cost-control and forecast reviews | Threshold/tolerance: ≤ 5% | Is the cost management variance within the approved tolerance, and what corrective action is required? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | ≤ 5% | ↓ Lower is better | Relative difference between planned and actual cost. A decline generally indicates improving control or less exposure. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | ₹9.6Cr vs ₹10Cr | −4% | 5
KPI-028 | Cost Management | Cost Savings | Measures realized savings against the approved cost baseline. | Planned cost − actual cost | Lagging / performance | Always-on | Planning through execution; use in weekly cost-control and forecast reviews | Threshold/tolerance: ≥ 0 | Are we within cost plan, and is corrective action needed to protect the budget? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | ≥ 0 | ↑ Higher is better | Measures realized savings against the approved cost baseline. An increase generally indicates stronger performance or control. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | Planned ₹10Cr; actual ₹9.4Cr | ₹0.6Cr | 5
KPI-029 | Cost Management | Cost Variance at Completion | Measures expected final cost deviation from budget. | EAC − BAC | Lagging / outcome | Trigger-based | Planning through execution; use in weekly cost-control and forecast reviews | Threshold/tolerance: ≤ 0 | Is the cost management variance within the approved tolerance, and what corrective action is required? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | ≤ 0 | ↓ Lower is better | Measures expected final cost deviation from budget. A decline generally indicates improving control or less exposure. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | EAC ₹10.3Cr; BAC ₹10Cr | +₹0.3Cr | 5
KPI-030 | Cost Management | Cash Flow Variance | Measures deviation between planned and actual cash expenditure. | Planned cash flow − actual cash flow | Lagging / performance | Trigger-based | Planning through execution; use in weekly cost-control and forecast reviews | Threshold/tolerance: Within tolerance | Is the cost management variance within the approved tolerance, and what corrective action is required? | Project Manager / Project Finance / PMO | Project financials / ERP / cost tracker / invoices | W | Within tolerance | ↔ Closer to 0 / within tolerance is better | Measures deviation between planned and actual cash expenditure. The preferred result is to remain close to the approved target or tolerance. | Investigate cost drivers, control spend, revise forecast, or escalate variance. | Plan ₹2.0Cr; actual ₹2.2Cr | −₹0.2Cr | 5
KPI-031 | Scope Management | Scope Stability Index | Measures how stable the approved project scope remains. | 1 − [scope changes ÷ total scope items] | Lagging / performance | Always-on | Initiation through execution; use during scope and change-control decisions | Threshold/tolerance: ≥ 90% | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | ≥ 90% | ↑ Higher is better | Measures how stable the approved project scope remains. An increase generally indicates stronger performance or control. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 8 changes across 160 scope items | 95% | 6
KPI-032 | Scope Management | Change Request Volume | Number of formal scope or requirement change requests. | Count of approved + rejected change requests | Lagging / performance | Always-on | Initiation through execution; use during scope and change-control decisions | Trigger on material adverse trend, exception, or management concern | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | Context-dependent | ↔ Context-dependent / target-driven | Number of formal scope or requirement change requests. The preferred result is to remain close to the approved target or tolerance. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | Requests logged this quarter | 18 | 6
KPI-033 | Scope Management | Scope Creep % | Uncontrolled scope added outside approved change control. | [Unapproved scope additions ÷ baseline scope] × 100 | Lagging / performance | Trigger-based | Initiation through execution; use during scope and change-control decisions | Threshold/tolerance: ≤ 5% | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | ≤ 5% | ↓ Lower is better | Uncontrolled scope added outside approved change control. A decline generally indicates improving control or less exposure. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 2 unapproved items / 100 baseline | 2% | 6
KPI-034 | Scope Management | Approved Change Requests % | Percentage of submitted change requests approved through governance. | [Approved changes ÷ submitted changes] × 100 | Lagging / performance | Always-on | Initiation through execution; use during scope and change-control decisions | Trigger on material adverse trend, exception, or management concern | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | Context-dependent | ↔ Context-dependent / target-driven | Percentage of submitted change requests approved through governance. The preferred result is to remain close to the approved target or tolerance. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 12 approved of 18 submitted | 66.7% | 6
KPI-035 | Scope Management | Requirements Coverage | Percentage of approved requirements mapped to deliverables or tests. | [Requirements covered ÷ total requirements] × 100 | Lagging / performance | Always-on | Initiation through execution; use during scope and change-control decisions | Threshold/tolerance: ≥ 95% | Is coverage/traceability sufficient for the current project stage and control requirement? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | ≥ 95% | ↑ Higher is better | Percentage of approved requirements mapped to deliverables or tests. An increase generally indicates stronger performance or control. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 285 covered / 300 requirements | 95% | 6
KPI-036 | Scope Management | Requirements Traceability | Measures end-to-end traceability from requirement to validation. | [Traceable requirements ÷ total requirements] × 100 | Lagging / performance | Always-on | Initiation through execution; use during scope and change-control decisions | Threshold/tolerance: ≥ 95% | Is coverage/traceability sufficient for the current project stage and control requirement? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | ≥ 95% | ↑ Higher is better | Measures end-to-end traceability from requirement to validation. An increase generally indicates stronger performance or control. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 290 / 300 requirements traced | 96.7% | 6
KPI-037 | Scope Management | Requirements Volatility | Measures the rate at which requirements change. | [(New + changed requirements) ÷ baseline requirements] × 100 | Leading | Always-on | Initiation through execution; use during scope and change-control decisions | Threshold/tolerance: ≤ 10% | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | ≤ 10% | ↓ Lower is better | Measures the rate at which requirements change. A decline generally indicates improving control or less exposure. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 24 changes / 300 baseline reqs | 8% | 6
KPI-038 | Scope Management | Feature Completion % | Percentage of planned features completed and accepted. | [Accepted features ÷ planned features] × 100 | Lagging / outcome | Always-on | Initiation through execution; use during scope and change-control decisions | Threshold/tolerance: ≥ 95% | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | ≥ 95% | ↑ Higher is better | Percentage of planned features completed and accepted. An increase generally indicates stronger performance or control. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 95 accepted / 100 planned | 95% | 6
KPI-039 | Scope Management | Deliverable Acceptance Rate | Percentage of deliverables accepted at first submission. | [Accepted deliverables ÷ submitted deliverables] × 100 | Lagging / outcome | Always-on | Initiation through execution; use during scope and change-control decisions | Threshold/tolerance: ≥ 95% | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | ≥ 95% | ↑ Higher is better | Percentage of deliverables accepted at first submission. An increase generally indicates stronger performance or control. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 47 accepted / 50 submitted | 94% | 6
KPI-040 | Scope Management | Scope Fulfilment Index | Measures delivered scope against approved scope. | [Delivered scope ÷ planned scope] × 100 | Lagging / performance | Always-on | Initiation through execution; use during scope and change-control decisions | Threshold/tolerance: ≥ 100% | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | ≥ 100% | ↑ Higher is better | Measures delivered scope against approved scope. An increase generally indicates stronger performance or control. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 98 delivered / 100 planned | 98% | 6
KPI-041 | Scope Management | Scope Validation Rate | Percentage of delivered scope formally validated. | [Validated scope ÷ delivered scope] × 100 | Lagging / performance | Always-on | Initiation through execution; use during scope and change-control decisions | Threshold/tolerance: ≥ 95% | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | ≥ 95% | ↑ Higher is better | Percentage of delivered scope formally validated. An increase generally indicates stronger performance or control. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | 96 validated / 98 delivered | 98% | 6
KPI-042 | Scope Management | Backlog Size | Number of unresolved approved scope items remaining. | Count of open backlog items | Leading | Always-on | Initiation through execution; use during scope and change-control decisions | Trigger on material adverse trend, exception, or management concern | Is approved scope stable, traceable and being delivered without uncontrolled expansion? | Project Manager / Product Owner / PMO | Requirements repository / scope baseline / change log / backlog | W | Context-dependent | ↓ Lower is better | Number of unresolved approved scope items remaining. A decline generally indicates improving control or less exposure. | Assess change impact, enforce change control, resolve traceability gaps, or reprioritize scope. | Approved open scope items | 24 | 6
KPI-043 | Quality Management | Deliverable Quality Index | Composite assessment of deliverable quality against defined criteria. | Weighted quality score across criteria | Lagging / performance | Phase-specific | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≥ 90% | Is quality within the acceptance threshold for the current delivery gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≥ 90% | ↑ Higher is better | Composite assessment of deliverable quality against defined criteria. An increase generally indicates stronger performance or control. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | Weighted quality assessment | 92/100 | 7
KPI-044 | Quality Management | First Pass Acceptance Rate | Percentage of deliverables accepted without rework. | [First-pass acceptances ÷ submissions] × 100 | Lagging / outcome | Always-on | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≥ 90% | Is deliverable quality acceptable for the next project gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≥ 90% | ↑ Higher is better | Percentage of deliverables accepted without rework. An increase generally indicates stronger performance or control. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 45 first-pass / 50 submissions | 90% | 7
KPI-045 | Quality Management | Rework % | Percentage of delivery effort spent correcting or repeating work. | [Rework effort ÷ total effort] × 100 | Lagging / performance | Always-on | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≤ 10% | Is deliverable quality acceptable for the next project gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≤ 10% | ↓ Lower is better | Percentage of delivery effort spent correcting or repeating work. A decline generally indicates improving control or less exposure. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 40 rework hrs / 500 total | 8% | 7
KPI-046 | Quality Management | Defect Density | Number of defects relative to delivered size or volume. | Defects ÷ delivered units | Lagging / performance | Phase-specific | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≤ agreed threshold | Is quality within the acceptance threshold for the current delivery gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≤ agreed threshold | ↓ Lower is better | Number of defects relative to delivered size or volume. A decline generally indicates improving control or less exposure. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 20 defects / 1,000 units | 0.02/unit | 7
KPI-047 | Quality Management | Defect Injection Rate | Rate at which new defects are introduced. | New defects ÷ completed work units | Lagging / performance | Phase-specific | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≤ agreed threshold | Is quality within the acceptance threshold for the current delivery gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≤ agreed threshold | ↓ Lower is better | Rate at which new defects are introduced. A decline generally indicates improving control or less exposure. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 12 new defects / 600 work items | 0.02/item | 7
KPI-048 | Quality Management | Defect Leakage | Defects discovered after the intended test stage. | [Escaped defects ÷ total defects] × 100 | Lagging / performance | Trigger-based | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≤ 5% | Is quality within the acceptance threshold for the current delivery gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≤ 5% | ↓ Lower is better | Defects discovered after the intended test stage. A decline generally indicates improving control or less exposure. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 3 escaped / 60 total defects | 5% | 7
KPI-049 | Quality Management | Critical Defects | Number of unresolved critical-severity defects. | Count of critical open defects | Lagging / performance | Trigger-based | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: 0 at go-live | Is quality within the acceptance threshold for the current delivery gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | 0 at go-live | ↓ Lower is better | Number of unresolved critical-severity defects. A decline generally indicates improving control or less exposure. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | Open Sev-1/critical defects | 2 | 7
KPI-050 | Quality Management | Defect Resolution Time | Average time required to resolve a defect. | Total resolution time ÷ defects resolved | Lagging / performance | Phase-specific | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: Lower is better | Is quality within the acceptance threshold for the current delivery gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | Lower is better | ↓ Lower is better | Average time required to resolve a defect. A decline generally indicates improving control or less exposure. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 240 hrs / 30 defects | 8 hrs | 7
KPI-051 | Quality Management | Test Case Pass Rate | Percentage of executed tests that pass. | [Passed tests ÷ executed tests] × 100 | Lagging / performance | Phase-specific | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≥ 95% | Is quality within the acceptance threshold for the current delivery gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≥ 95% | ↑ Higher is better | Percentage of executed tests that pass. An increase generally indicates stronger performance or control. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 1,140 passed / 1,200 executed | 95% | 7
KPI-052 | Quality Management | Test Coverage % | Percentage of requirements or functionality covered by testing. | [Covered items ÷ total testable items] × 100 | Lagging / performance | Phase-specific | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≥ 95% | Is coverage/traceability sufficient for the current project stage and control requirement? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≥ 95% | ↑ Higher is better | Percentage of requirements or functionality covered by testing. An increase generally indicates stronger performance or control. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 285 covered / 300 requirements | 95% | 7
KPI-053 | Quality Management | Automation Coverage | Percentage of eligible tests automated. | [Automated tests ÷ eligible tests] × 100 | Lagging / performance | Always-on | Execution, testing/UAT, go-live and quality gates | Trigger on material adverse trend, exception, or management concern | Is coverage/traceability sufficient for the current project stage and control requirement? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | Context-dependent | ↑ Higher is better | Percentage of eligible tests automated. An increase generally indicates stronger performance or control. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 420 automated / 600 eligible | 70% | 7
KPI-054 | Quality Management | Code Quality Score | Measures code against defined quality and engineering standards. | Quality assessment score | Lagging / outcome | Phase-specific | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≥ 80% | Is quality within the acceptance threshold for the current delivery gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≥ 80% | ↑ Higher is better | Measures code against defined quality and engineering standards. An increase generally indicates stronger performance or control. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | Static analysis score | 88/100 | 7
KPI-055 | Quality Management | Review Effectiveness | Percentage of defects identified during review before downstream testing. | [Review defects found ÷ total defects] × 100 | Lagging / outcome | Always-on | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≥ 80% | Is deliverable quality acceptable for the next project gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≥ 80% | ↑ Higher is better | Percentage of defects identified during review before downstream testing. An increase generally indicates stronger performance or control. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 80 review-found / 100 total defects | 80% | 7
KPI-056 | Quality Management | Customer Acceptance Rate | Percentage of deliverables accepted by the customer or sponsor. | [Accepted deliverables ÷ submitted deliverables] × 100 | Lagging / outcome | Phase-specific | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≥ 95% | Is deliverable quality acceptable for the next project gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≥ 95% | ↑ Higher is better | Percentage of deliverables accepted by the customer or sponsor. An increase generally indicates stronger performance or control. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 47 accepted / 50 deliverables | 94% | 7
KPI-057 | Quality Management | Compliance Score | Percentage of applicable quality/compliance controls satisfied. | [Compliant controls ÷ applicable controls] × 100 | Lagging / outcome | Always-on | Execution, testing/UAT, go-live and quality gates | Threshold/tolerance: ≥ 95% | Is deliverable quality acceptable for the next project gate? | Quality Lead / Test Lead / Project Manager | Quality dashboard / defect log / test management tool / reviews | W | ≥ 95% | ↑ Higher is better | Percentage of applicable quality/compliance controls satisfied. An increase generally indicates stronger performance or control. | Contain defects, increase testing/review coverage, reduce rework, or block the next gate. | 190 compliant / 200 controls | 95% | 7
KPI-058 | Risk & Issue Management | Number of Open Risks | Current count of identified risks without closure. | Count of open risks | Leading | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Trigger on material adverse trend, exception, or management concern | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | Context-dependent | ↓ Lower is better | Current count of identified risks without closure. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | Current risk register | 14 | 8
KPI-059 | Risk & Issue Management | Risk Exposure Score | Aggregate exposure based on probability and impact. | Σ[Probability × Impact] | Leading | Trigger-based | All phases, with heightened use at governance and delivery-risk reviews | Trigger on material adverse trend, exception, or management concern | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | Context-dependent | ↓ Lower is better | Aggregate exposure based on probability and impact. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | Σ probability × impact | ₹1.2Cr | 8
KPI-060 | Risk & Issue Management | High-Risk Count | Number of risks above the defined high-risk threshold. | Count of high/critical risks | Leading | Trigger-based | All phases, with heightened use at governance and delivery-risk reviews | Trigger on adverse upward trend or breach of risk threshold | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | Trending down | ↓ Lower / downward trend is better | Number of risks above the defined high-risk threshold. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | High/critical risks | 3 | 8
KPI-061 | Risk & Issue Management | Risk Closure Rate | Percentage of identified risks closed during the period. | [Risks closed ÷ risks due for closure] × 100 | Leading | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: ≥ 90% | Are risk & issue management items being resolved/closed fast enough, and where is intervention needed? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | ≥ 90% | ↑ Higher is better | Percentage of identified risks closed during the period. An increase generally indicates stronger performance or control. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 18 closed / 20 due | 90% | 8
KPI-062 | Risk & Issue Management | Average Risk Resolution Time | Average time to resolve or retire a risk. | Total risk resolution days ÷ risks closed | Leading | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: Lower is better | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | Lower is better | ↓ Lower is better | Average time to resolve or retire a risk. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 360 days? no; 90 days / 10 risks | 9 days | 8
KPI-063 | Risk & Issue Management | Risk Aging | Average age of unresolved risks. | Σ age of open risks ÷ open risks | Leading | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: Lower is better | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | Lower is better | ↓ Lower is better | Average age of unresolved risks. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 180 days / 20 open risks | 9 days | 8
KPI-064 | Risk & Issue Management | Number of Open Issues | Current count of unresolved project issues. | Count of open issues | Lagging / performance | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Trigger on material adverse trend, exception, or management concern | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | Context-dependent | ↓ Lower is better | Current count of unresolved project issues. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | Issue log | 11 | 8
KPI-065 | Risk & Issue Management | Issue Closure Rate | Percentage of issues closed during the period. | [Issues closed ÷ issues due for closure] × 100 | Lagging / performance | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: ≥ 90% | Are risk & issue management items being resolved/closed fast enough, and where is intervention needed? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | ≥ 90% | ↑ Higher is better | Percentage of issues closed during the period. An increase generally indicates stronger performance or control. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 27 closed / 30 due | 90% | 8
KPI-066 | Risk & Issue Management | Average Issue Resolution Time | Average elapsed time from issue identification to closure. | Total issue resolution days ÷ issues closed | Lagging / performance | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: Lower is better | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | Lower is better | ↓ Lower is better | Average elapsed time from issue identification to closure. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 240 days / 20 issues | 12 days | 8
KPI-067 | Risk & Issue Management | Escalation Rate | Percentage of issues requiring escalation beyond the working team. | [Escalated issues ÷ total issues] × 100 | Lagging / performance | Trigger-based | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: ≤ 10% | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | ≤ 10% | ↓ Lower is better | Percentage of issues requiring escalation beyond the working team. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 3 escalations / 30 issues | 10% | 8
KPI-068 | Risk & Issue Management | Mitigation Effectiveness | Measures whether implemented risk responses reduce exposure. | [Risks with effective mitigation ÷ mitigated risks[ × 100 | Lagging / outcome | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: ≥ 90% | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | ≥ 90% | ↑ Higher is better | Measures whether implemented risk responses reduce exposure. An increase generally indicates stronger performance or control. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 18 effective / 20 mitigated | 90% | 8
KPI-069 | Risk & Issue Management | Contingency Utilization % | Percentage of allocated contingency consumed. | [Contingency used ÷ contingency allocated] × 100 | Leading | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: ≤ 80% | Do we have the right capacity and allocation to sustain delivery? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | ≤ 80% | ↓ Lower is better | Percentage of allocated contingency consumed. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | ₹0.8Cr used / ₹1Cr | 80% | 8
KPI-070 | Risk & Issue Management | Assumption Validation Rate | Percentage of critical assumptions formally validated. | [Validated assumptions ÷ critical assumptions] × 100 | Lagging / performance | Always-on | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: ≥ 95% | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | ≥ 95% | ↑ Higher is better | Percentage of critical assumptions formally validated. An increase generally indicates stronger performance or control. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 95 validated / 100 | 95% | 8
KPI-071 | Risk & Issue Management | Dependency at Risk % | Percentage of dependencies currently threatening delivery. | [At-risk dependencies ÷ total dependencies] × 100 | Leading | Trigger-based | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: ≤ 10% | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | ≤ 10% | ↓ Lower is better | Percentage of dependencies currently threatening delivery. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 4 at-risk / 40 dependencies | 10% | 8
KPI-072 | Risk & Issue Management | Issue Reopen Rate | Percentage of closed issues that are reopened. | [Reopened issues ÷ closed issues] × 100 | Lagging / performance | Trigger-based | All phases, with heightened use at governance and delivery-risk reviews | Threshold/tolerance: ≤ 5% | What emerging risk or issue requires intervention or escalation? | Project Manager / Risk & Issue Lead | RAID log / issue register / risk register / dependency log | W | ≤ 5% | ↓ Lower is better | Percentage of closed issues that are reopened. A decline generally indicates improving control or less exposure. | Assign mitigation/owner, escalate, consume contingency where approved, or revise the delivery plan. | 1 reopened / 20 closed | 5% | 8
KPI-073 | Resource Management | Resource Utilization | Percentage of available resource capacity used for project work. | [Actual project hours ÷ available hours] × 100 | Leading | Always-on | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: 80–100% | Do we have the right capacity and allocation to sustain delivery? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | 80–100% | ↔ Within target range | Percentage of available resource capacity used for project work. The preferred result is to remain close to the approved target or tolerance. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 1,520 project hrs / 1,800 available | 84.4% | 9
KPI-074 | Resource Management | Capacity Utilization | Percentage of available team capacity allocated. | [Used capacity ÷ total capacity] × 100 | Leading | Always-on | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: 80–100% | Do we have the right capacity and allocation to sustain delivery? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | 80–100% | ↔ Within target range | Percentage of available team capacity allocated. The preferred result is to remain close to the approved target or tolerance. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 1,600 allocated / 1,800 capacity | 88.9% | 9
KPI-075 | Resource Management | Overallocation % | Percentage of resource capacity allocated above availability. | [Overallocated capacity ÷ total capacity] × 100 | Leading | Trigger-based | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: ≤ 10% | Do we have the right capacity, skills and cost profile to deliver the plan? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | ≤ 10% | ↓ Lower is better | Percentage of resource capacity allocated above availability. A decline generally indicates improving control or less exposure. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 90 overallocated hrs / 1,800 | 5% | 9
KPI-076 | Resource Management | Underutilization % | Percentage of available capacity not assigned to project work. | [Unused capacity ÷ total capacity] × 100 | Leading | Trigger-based | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: ≤ 10% | Do we have the right capacity and allocation to sustain delivery? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | ≤ 10% | ↓ Lower is better | Percentage of available capacity not assigned to project work. A decline generally indicates improving control or less exposure. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 144 unused hrs / 1,800 | 8% | 9
KPI-077 | Resource Management | Team Availability | Percentage of required resource capacity available. | [Available required capacity ÷ total required capacity] × 100 | Leading | Always-on | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: ≥ 90% | Do we have the right capacity and allocation to sustain delivery? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | ≥ 90% | ↑ Higher is better | Percentage of required resource capacity available. An increase generally indicates stronger performance or control. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 180 available / 200 required days | 90% | 9
KPI-078 | Resource Management | Attrition Rate | Percentage of project resources leaving during a period. | [Exits ÷ average headcount] × 100 | Lagging / performance | Always-on | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: ≤ 10% | Do we have the right capacity, skills and cost profile to deliver the plan? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | ≤ 10% | ↓ Lower is better | Percentage of project resources leaving during a period. A decline generally indicates improving control or less exposure. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 2 exits / avg 40 FTE | 5% | 9
KPI-079 | Resource Management | Vacancy Rate | Percentage of approved project positions not filled. | [Open positions ÷ approved positions] × 100 | Lagging / performance | Always-on | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: ≤ 10% | Do we have the right capacity, skills and cost profile to deliver the plan? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | ≤ 10% | ↓ Lower is better | Percentage of approved project positions not filled. A decline generally indicates improving control or less exposure. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 2 open / 40 approved roles | 5% | 9
KPI-080 | Resource Management | Resource Fill Time | Average time required to fill a project resource requirement. | Σ days to fill ÷ positions filled | Lagging / performance | Always-on | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: Lower is better | Do we have the right capacity, skills and cost profile to deliver the plan? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | Lower is better | ↓ Lower is better | Average time required to fill a project resource requirement. A decline generally indicates improving control or less exposure. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 60 days / 6 positions | 10 days | 9
KPI-081 | Resource Management | Skill Adequacy Index | Measures availability of required skills within the project team. | [Available required skills ÷ total required skills] × 100 | Lagging / performance | Always-on | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: ≥ 90% | Do we have the right capacity, skills and cost profile to deliver the plan? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | ≥ 90% | ↑ Higher is better | Measures availability of required skills within the project team. An increase generally indicates stronger performance or control. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 18 of 20 required skills | 90% | 9
KPI-082 | Resource Management | Training Hours per Resource | Average training time provided to project resources. | Total training hours ÷ project resources | Lagging / performance | Always-on | Planning, mobilisation and execution; use in capacity and staffing reviews | Trigger on material adverse trend, exception, or management concern | Do we have the right capacity, skills and cost profile to deliver the plan? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | Context-dependent | ↔ Context-dependent / target-driven | Average training time provided to project resources. The preferred result is to remain close to the approved target or tolerance. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 240 hrs / 40 resources | 6 hrs/resource | 9
KPI-083 | Resource Management | Resource Productivity | Measures delivered work relative to resource effort. | Output units ÷ resource hours | Lagging / performance | Always-on | Planning, mobilisation and execution; use in capacity and staffing reviews | Trigger on adverse downward trend or missed improvement trajectory | Do we have the right capacity, skills and cost profile to deliver the plan? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | Trending up | ↑ Higher / upward trend is better | Measures delivered work relative to resource effort. An increase generally indicates stronger performance or control. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | 800 work units / 1,600 hrs | 0.5 units/hr | 9
KPI-084 | Resource Management | Resource Cost Variance | Difference between planned and actual resource cost. | Planned resource cost − actual resource cost | Lagging / performance | Trigger-based | Planning, mobilisation and execution; use in capacity and staffing reviews | Threshold/tolerance: Within tolerance | Is the resource management variance within the approved tolerance, and what corrective action is required? | Project Manager / Resource Manager / PMO | Resource plan / capacity tracker / timesheets / staffing report | W | Within tolerance | ↔ Closer to 0 / within tolerance is better | Difference between planned and actual resource cost. The preferred result is to remain close to the approved target or tolerance. | Rebalance capacity, fill vacancies, address skill gaps, reduce over-allocation, or adjust staffing. | ₹4.2Cr plan; ₹4.4Cr actual | −₹0.2Cr | 9
KPI-085 | Stakeholder Management | Stakeholder Satisfaction Index | Average stakeholder rating of project performance. | Σ stakeholder ratings ÷ number of ratings | Lagging / outcome | Always-on | All phases, especially governance, decision and change-impact points | Threshold/tolerance: ≥ 4.0 / 5 | Are stakeholders sufficiently satisfied, confident and aligned to support delivery? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | ≥ 4.0 / 5 | ↑ Higher is better | Average stakeholder rating of project performance. An increase generally indicates stronger performance or control. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | Average survey score | 4.2/5 | 10
KPI-086 | Stakeholder Management | Sponsor Engagement Score | Measures sponsor participation and responsiveness. | Weighted sponsor engagement score | Lagging / performance | Always-on | All phases, especially governance, decision and change-impact points | Threshold/tolerance: ≥ 80 / 100 | Are stakeholders aligned, engaged and confident enough to support delivery? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | ≥ 80 / 100 | ↑ Higher is better | Measures sponsor participation and responsiveness. An increase generally indicates stronger performance or control. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | Weighted sponsor score | 86/100 | 10
KPI-087 | Stakeholder Management | Executive Participation % | Percentage of required executive interactions attended. | [Executive attendance ÷ required attendance] × 100 | Lagging / performance | Always-on | All phases, especially governance, decision and change-impact points | Threshold/tolerance: ≥ 90% | Are stakeholders aligned, engaged and confident enough to support delivery? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | ≥ 90% | ↑ Higher is better | Percentage of required executive interactions attended. An increase generally indicates stronger performance or control. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | 18 attended / 20 required | 90% | 10
KPI-088 | Stakeholder Management | Decision Turnaround Time | Average time from decision request to decision. | Σ decision days ÷ decisions made | Leading | Always-on | All phases, especially governance, decision and change-impact points | Threshold/tolerance: Lower is better | Are stakeholders aligned, engaged and confident enough to support delivery? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | Lower is better | ↓ Lower is better | Average time from decision request to decision. A decline generally indicates improving control or less exposure. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | 120 days / 15 decisions | 8 days | 10
KPI-089 | Stakeholder Management | Escalation Resolution Time | Average time to resolve escalated stakeholder matters. | Σ escalation resolution days ÷ escalations closed | Lagging / performance | Trigger-based | All phases, especially governance, decision and change-impact points | Threshold/tolerance: Lower is better | Are stakeholders aligned, engaged and confident enough to support delivery? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | Lower is better | ↓ Lower is better | Average time to resolve escalated stakeholder matters. A decline generally indicates improving control or less exposure. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | 45 days / 5 escalations | 9 days | 10
KPI-090 | Stakeholder Management | Stakeholder Influence Index | Weighted measure of stakeholder influence and engagement. | Weighted influence score | Lagging / performance | Always-on | All phases, especially governance, decision and change-impact points | Threshold/tolerance: ≥ 80 / 100 | Are stakeholders aligned, engaged and confident enough to support delivery? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | ≥ 80 / 100 | ↑ Higher is better | Weighted measure of stakeholder influence and engagement. An increase generally indicates stronger performance or control. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | Weighted stakeholder score | 82/100 | 10
KPI-091 | Stakeholder Management | Stakeholder Confidence Score | Measures confidence in project delivery. | Average confidence survey score | Lagging / outcome | Always-on | All phases, especially governance, decision and change-impact points | Threshold/tolerance: ≥ 80 / 100 | Are stakeholders sufficiently satisfied, confident and aligned to support delivery? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | ≥ 80 / 100 | ↑ Higher is better | Measures confidence in project delivery. An increase generally indicates stronger performance or control. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | Stakeholder pulse | 84/100 | 10
KPI-092 | Stakeholder Management | Stakeholder Communication Satisfaction | Stakeholder rating of project communication quality. | Σ communication ratings ÷ respondents | Lagging / outcome | Always-on | All phases, especially governance, decision and change-impact points | Threshold/tolerance: ≥ 4.0 / 5 | Are stakeholders sufficiently satisfied, confident and aligned to support delivery? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | ≥ 4.0 / 5 | ↑ Higher is better | Stakeholder rating of project communication quality. An increase generally indicates stronger performance or control. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | Average communication rating | 4.1/5 | 10
KPI-093 | Stakeholder Management | Change Impact Coverage | Percentage of identified stakeholder groups assessed for project impact. | [Impacted groups assessed ÷ impacted groups identified] × 100 | Lagging / performance | Always-on | All phases, especially governance, decision and change-impact points | Threshold/tolerance: ≥ 95% | Is coverage/traceability sufficient for the current project stage and control requirement? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | ≥ 95% | ↑ Higher is better | Percentage of identified stakeholder groups assessed for project impact. An increase generally indicates stronger performance or control. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | 47 groups assessed / 50 | 94% | 10
KPI-094 | Stakeholder Management | Stakeholder Alignment Score | Measures agreement on objectives, scope and key decisions. | Alignment survey score | Lagging / performance | Always-on | All phases, especially governance, decision and change-impact points | Threshold/tolerance: ≥ 80 / 100 | Are stakeholders sufficiently satisfied, confident and aligned to support delivery? | Project Manager / Sponsor / Change Lead | Stakeholder register / surveys / pulse checks / governance records | W | ≥ 80 / 100 | ↑ Higher is better | Measures agreement on objectives, scope and key decisions. An increase generally indicates stronger performance or control. | Target engagement, resolve alignment gaps, accelerate decisions, or escalate stakeholder concerns. | Alignment pulse | 88/100 | 10
KPI-095 | Communication Management | Communication Effectiveness | Measures whether project communications are understood and useful. | Communication effectiveness score | Lagging / outcome | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≥ 80 / 100 | Are project communications timely, accurate, understood and reaching the intended audience? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≥ 80 / 100 | ↑ Higher is better | Measures whether project communications are understood and useful. An increase generally indicates stronger performance or control. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | Communication pulse | 85/100 | 11
KPI-096 | Communication Management | Status Report Timeliness | Percentage of project reports issued by the agreed deadline. | [On-time reports ÷ planned reports] × 100 | Lagging / performance | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≥ 95% | Are project communications timely, accurate, understood and reaching the intended audience? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≥ 95% | ↑ Higher is better | Percentage of project reports issued by the agreed deadline. An increase generally indicates stronger performance or control. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | 19 on-time / 20 reports | 95% | 11
KPI-097 | Communication Management | Communication Reach % | Percentage of intended recipients reached. | [Recipients reached ÷ intended recipients] × 100 | Lagging / performance | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≥ 95% | Are project communications timely, accurate, understood and reaching the intended audience? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≥ 95% | ↑ Higher is better | Percentage of intended recipients reached. An increase generally indicates stronger performance or control. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | 950 reached / 1,000 | 95% | 11
KPI-098 | Communication Management | Information Accuracy | Percentage of sampled communications found to be accurate. | [Accurate communications ÷ sampled communications] × 100 | Lagging / performance | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≥ 95% | Are project communications timely, accurate, understood and reaching the intended audience? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≥ 95% | ↑ Higher is better | Percentage of sampled communications found to be accurate. An increase generally indicates stronger performance or control. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | 97 accurate / 100 sampled | 97% | 11
KPI-099 | Communication Management | Message Recall Rate | Percentage of recipients able to recall key project messages. | [Recipients recalling message ÷ respondents] × 100 | Lagging / performance | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≥ 80% | Are project communications timely, accurate, understood and reaching the intended audience? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≥ 80% | ↑ Higher is better | Percentage of recipients able to recall key project messages. An increase generally indicates stronger performance or control. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | 80 of 100 recall key message | 80% | 11
KPI-100 | Communication Management | Meeting Effectiveness | Measures whether meetings achieve intended objectives. | Meeting effectiveness score | Lagging / outcome | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≥ 80 / 100 | Are project communications timely, accurate, understood and reaching the intended audience? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≥ 80 / 100 | ↑ Higher is better | Measures whether meetings achieve intended objectives. An increase generally indicates stronger performance or control. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | Meeting pulse score | 82/100 | 11
KPI-101 | Communication Management | Meeting Attendance Rate | Percentage of required participants attending key meetings. | [Attendees ÷ required attendees] × 100 | Lagging / performance | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≥ 90% | Are project communications timely, accurate, understood and reaching the intended audience? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≥ 90% | ↑ Higher is better | Percentage of required participants attending key meetings. An increase generally indicates stronger performance or control. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | 90 attendees / 100 expected | 90% | 11
KPI-102 | Communication Management | Action Item Closure Rate | Percentage of meeting actions closed by due date. | [Actions closed on time ÷ actions due] × 100 | Lagging / performance | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≥ 90% | Are communication management items being resolved/closed fast enough, and where is intervention needed? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≥ 90% | ↑ Higher is better | Percentage of meeting actions closed by due date. An increase generally indicates stronger performance or control. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | 45 closed / 50 due | 90% | 11
KPI-103 | Communication Management | Response Time to Queries | Average time to respond to project queries. | Σ response hours ÷ queries answered | Lagging / performance | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≤ agreed SLA | Are project communications timely, accurate, understood and reaching the intended audience? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≤ agreed SLA | ↓ Lower is better | Average time to respond to project queries. A decline generally indicates improving control or less exposure. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | 240 hrs / 40 queries | 6 hrs | 11
KPI-104 | Communication Management | Communication Plan Adherence | Percentage of planned communications delivered as scheduled. | [Communications delivered ÷ planned communications] × 100 | Lagging / performance | Always-on | Mobilisation through execution and governance | Threshold/tolerance: ≥ 95% | Are project communications timely, accurate, understood and reaching the intended audience? | Project Manager / PMO / Communications Lead | Communication plan / status reports / meeting records / communication analytics | W | ≥ 95% | ↑ Higher is better | Percentage of planned communications delivered as scheduled. An increase generally indicates stronger performance or control. | Correct communication gaps, change channels/cadence, clarify messages, or close overdue actions. | 19 delivered / 20 planned | 95% | 11
KPI-105 | Procurement & Contract Management | Vendor SLA Compliance | Percentage of contracted service levels met. | [SLAs met ÷ SLAs measured] × 100 | Lagging / outcome | Phase-specific | Procurement, contracting and vendor execution | Threshold/tolerance: ≥ 95% | Are vendors and contracts meeting agreed commercial and delivery commitments? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | ≥ 95% | ↑ Higher is better | Percentage of contracted service levels met. An increase generally indicates stronger performance or control. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | 95 SLAs met / 100 | 95% | 12
KPI-106 | Procurement & Contract Management | Vendor Delivery Performance | Measures vendor performance against agreed delivery commitments. | [Vendor commitments met ÷ commitments due] × 100 | Lagging / performance | Phase-specific | Procurement, contracting and vendor execution | Threshold/tolerance: ≥ 90% | Are vendors and contracts meeting agreed commercial and delivery commitments? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | ≥ 90% | ↑ Higher is better | Measures vendor performance against agreed delivery commitments. An increase generally indicates stronger performance or control. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | 27 commitments met / 30 | 90% | 12
KPI-107 | Procurement & Contract Management | Contract Compliance | Percentage of sampled contract obligations complied with. | [Compliant obligations ÷ obligations tested] × 100 | Lagging / outcome | Phase-specific | Procurement, contracting and vendor execution | Threshold/tolerance: ≥ 95% | Are vendors and contracts meeting agreed commercial and delivery commitments? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | ≥ 95% | ↑ Higher is better | Percentage of sampled contract obligations complied with. An increase generally indicates stronger performance or control. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | 95 obligations / 100 | 95% | 12
KPI-108 | Procurement & Contract Management | Procurement Cycle Time | Average time from approved request to purchase order or award. | Σ procurement days ÷ procurements completed | Leading | Phase-specific | Procurement, contracting and vendor execution | Threshold/tolerance: Lower is better | Are vendors and contracts meeting agreed commercial and delivery commitments? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | Lower is better | ↓ Lower is better | Average time from approved request to purchase order or award. A decline generally indicates improving control or less exposure. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | 300 days / 30 procurements | 10 days | 12
KPI-109 | Procurement & Contract Management | PO / Purchase Order Cycle Time | Time from purchase request to purchase order issuance. | PO issue date − request date | Leading | Phase-specific | Procurement, contracting and vendor execution | Threshold/tolerance: Lower is better | Are vendors and contracts meeting agreed commercial and delivery commitments? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | Lower is better | ↓ Lower is better | Time from purchase request to purchase order issuance. A decline generally indicates improving control or less exposure. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | 150 days / 30 POs | 5 days | 12
KPI-110 | Procurement & Contract Management | Procurement Cost Variance | Difference between planned and actual procurement cost. | Actual procurement cost − planned cost | Lagging / performance | Trigger-based | Procurement, contracting and vendor execution | Threshold/tolerance: ≤ 5% | Is the procurement & contract management variance within the approved tolerance, and what corrective action is required? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | ≤ 5% | ↓ Lower is better | Difference between planned and actual procurement cost. A decline generally indicates improving control or less exposure. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | ₹2.1Cr actual vs ₹2Cr plan | +₹0.1Cr | 12
KPI-111 | Procurement & Contract Management | Invoice Accuracy % | Percentage of invoices processed without correction. | [Accurate invoices ÷ invoices processed] × 100 | Lagging / performance | Phase-specific | Procurement, contracting and vendor execution | Threshold/tolerance: ≥ 95% | Are vendors and contracts meeting agreed commercial and delivery commitments? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | ≥ 95% | ↑ Higher is better | Percentage of invoices processed without correction. An increase generally indicates stronger performance or control. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | 190 accurate / 200 | 95% | 12
KPI-112 | Procurement & Contract Management | Payment On-Time % | Percentage of valid invoices paid within agreed terms. | [On-time payments ÷ payments due] × 100 | Lagging / performance | Phase-specific | Procurement, contracting and vendor execution | Threshold/tolerance: ≥ 95% | Are vendors and contracts meeting agreed commercial and delivery commitments? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | ≥ 95% | ↑ Higher is better | Percentage of valid invoices paid within agreed terms. An increase generally indicates stronger performance or control. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | 190 on-time / 200 | 95% | 12
KPI-113 | Procurement & Contract Management | Vendor Relationship Score | Assessment of vendor relationship effectiveness. | Weighted relationship score | Lagging / performance | Phase-specific | Procurement, contracting and vendor execution | Threshold/tolerance: ≥ 80 / 100 | Are vendors and contracts meeting agreed commercial and delivery commitments? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | ≥ 80 / 100 | ↑ Higher is better | Assessment of vendor relationship effectiveness. An increase generally indicates stronger performance or control. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | Quarterly vendor score | 84/100 | 12
KPI-114 | Procurement & Contract Management | Contract Renewal Timeliness | Percentage of renewals completed before contractual deadlines. | [On-time renewals ÷ renewals due] × 100 | Lagging / performance | Phase-specific | Procurement, contracting and vendor execution | Threshold/tolerance: ≥ 90% | Are vendors and contracts meeting agreed commercial and delivery commitments? | Procurement Lead / Contract Manager / Project Manager | Procurement system / PO records / contracts / vendor scorecards / invoices | W | ≥ 90% | ↑ Higher is better | Percentage of renewals completed before contractual deadlines. An increase generally indicates stronger performance or control. | Resolve vendor performance issues, enforce contract terms, expedite procurement, or escalate commercial risks. | 9 on-time / 10 renewals | 90% | 12
KPI-115 | Agile Delivery KPIs | Velocity | Amount of work completed by the team per sprint. | Story points completed per sprint | Lagging / performance | Phase-specific | Sprint planning, execution, review and retrospective | Trigger on material volatility or loss of predictability | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | Stable / predictable | ↔ Stability / predictability is better | Amount of work completed by the team per sprint. The preferred result is to remain close to the approved target or tolerance. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | Average over 6 sprints | 34 pts/sprint | 13
KPI-116 | Agile Delivery KPIs | Sprint Goal Achievement % | Percentage of sprint goals fully achieved. | [Goals achieved ÷ goals committed] × 100 | Lagging / outcome | Phase-specific | Sprint planning, execution, review and retrospective | Threshold/tolerance: ≥ 90% | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | ≥ 90% | ↑ Higher is better | Percentage of sprint goals fully achieved. An increase generally indicates stronger performance or control. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | 9 goals achieved / 10 | 90% | 13
KPI-117 | Agile Delivery KPIs | Sprint Burndown | Tracks remaining work against the sprint plan. | Remaining work by day | Lagging / performance | Phase-specific | Sprint planning, execution, review and retrospective | Trigger on material adverse trend, exception, or management concern | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | Context-dependent | ↔ Context-dependent / target-driven | Tracks remaining work against the sprint plan. The preferred result is to remain close to the approved target or tolerance. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | Day 8 remaining work | 18 pts | 13
KPI-118 | Agile Delivery KPIs | Sprint Burnup | Tracks completed work against total sprint scope. | Completed work over time | Lagging / performance | Phase-specific | Sprint planning, execution, review and retrospective | Trigger on material adverse trend, exception, or management concern | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | Context-dependent | ↔ Context-dependent / target-driven | Tracks completed work against total sprint scope. The preferred result is to remain close to the approved target or tolerance. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | Completed of total scope | 82/100 pts | 13
KPI-119 | Agile Delivery KPIs | Story Completion Rate | Percentage of committed stories completed within the sprint. | [Completed stories ÷ committed stories] × 100 | Lagging / outcome | Phase-specific | Sprint planning, execution, review and retrospective | Threshold/tolerance: ≥ 90% | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | ≥ 90% | ↑ Higher is better | Percentage of committed stories completed within the sprint. An increase generally indicates stronger performance or control. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | 45 stories / 50 committed | 90% | 13
KPI-120 | Agile Delivery KPIs | Escaped Defects | Defects discovered after the sprint or planned test stage. | Count of escaped defects | Lagging / performance | Phase-specific | Sprint planning, execution, review and retrospective | Trigger on adverse upward trend or breach of risk threshold | Is quality within the acceptance threshold for the current delivery gate? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | Trending down | ↓ Lower / downward trend is better | Defects discovered after the sprint or planned test stage. A decline generally indicates improving control or less exposure. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | Defects after sprint | 3 | 13
KPI-121 | Agile Delivery KPIs | Sprint Predictability | Measures consistency between committed and delivered work. | [Delivered committed points ÷ committed points] × 100 | Lagging / performance | Phase-specific | Sprint planning, execution, review and retrospective | Threshold/tolerance: ≥ 85% | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | ≥ 85% | ↑ Higher is better | Measures consistency between committed and delivered work. An increase generally indicates stronger performance or control. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | 34 of 40 committed points | 85% | 13
KPI-122 | Agile Delivery KPIs | Commitment Accuracy | Measures reliability of sprint commitments. | [Committed work delivered ÷ committed work] × 100 | Lagging / performance | Phase-specific | Sprint planning, execution, review and retrospective | Threshold/tolerance: ≥ 85% | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | ≥ 85% | ↑ Higher is better | Measures reliability of sprint commitments. An increase generally indicates stronger performance or control. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | 34 delivered / 40 committed pts | 85% | 13
KPI-123 | Agile Delivery KPIs | Lead Time (Agile) | Elapsed time from work item approval to completion. | Completion date − approval date | Leading | Phase-specific | Sprint planning, execution, review and retrospective | Threshold/tolerance: Lower is better | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | Lower is better | ↓ Lower is better | Elapsed time from work item approval to completion. A decline generally indicates improving control or less exposure. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | Approval to done | 6 days | 13
KPI-124 | Agile Delivery KPIs | Cycle Time (Agile) | Elapsed time from work start to completion. | Completion date − start date | Leading | Phase-specific | Sprint planning, execution, review and retrospective | Threshold/tolerance: Lower is better | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | Lower is better | ↓ Lower is better | Elapsed time from work start to completion. A decline generally indicates improving control or less exposure. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | Start to done | 3 days | 13
KPI-125 | Agile Delivery KPIs | Retrospective Action Rate | Percentage of retrospective actions completed. | [Actions closed ÷ actions raised] × 100 | Lagging / performance | Phase-specific | Sprint planning, execution, review and retrospective | Threshold/tolerance: ≥ 90% | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | ≥ 90% | ↑ Higher is better | Percentage of retrospective actions completed. An increase generally indicates stronger performance or control. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | 18 actions closed / 20 | 90% | 13
KPI-126 | Agile Delivery KPIs | Team Happiness / Health | Pulse measure of team health, sustainability and morale. | Average team pulse score | Lagging / outcome | Phase-specific | Sprint planning, execution, review and retrospective | Threshold/tolerance: ≥ 4.0 / 5 | Is the team delivering committed value predictably and sustainably? | Product Owner / Scrum Master / Delivery Lead | Agile tool / sprint board / backlog / team pulse | W | ≥ 4.0 / 5 | ↑ Higher is better | Pulse measure of team health, sustainability and morale. An increase generally indicates stronger performance or control. | Rebalance sprint scope, remove impediments, improve flow, address defects, or adapt commitments. | Team pulse | 4.1/5 | 13
KPI-127 | Financial Forecasting | Estimate at Completion (EAC) | Forecast of total project cost at completion. | AC + [BAC − EV] ÷ CPI | Lagging / outcome | Always-on | Planning and execution; especially monthly forecasting and financial governance | Trigger on material adverse trend, exception, or management concern | What is the latest expected outcome, and is corrective action needed now? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | Context-dependent | ↑ Higher is better | Forecast of total project cost at completion. An increase generally indicates stronger performance or control. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | AC ₹9.6Cr; BAC ₹10Cr; CPI 0.94 | ₹10.0Cr | 14
KPI-128 | Financial Forecasting | Estimate to Complete (ETC) | Forecast of remaining project cost. | EAC − AC | Lagging / performance | Always-on | Planning and execution; especially monthly forecasting and financial governance | Trigger on material adverse trend, exception, or management concern | What is the latest expected outcome, and is corrective action needed now? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | Context-dependent | ↔ Context-dependent / target-driven | Forecast of remaining project cost. The preferred result is to remain close to the approved target or tolerance. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | EAC ₹10.2Cr; AC ₹9.6Cr | ₹0.6Cr | 14
KPI-129 | Financial Forecasting | To Complete Performance Index (TCPI) | Cost efficiency required to meet a budget target. | [BAC − EV] ÷ [EAC − AC] | Lagging / performance | Always-on | Planning and execution; especially monthly forecasting and financial governance | Threshold/tolerance: ≥ 1.00 | What is the expected final financial position and what action is required now? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | ≥ 1.00 | ↑ Higher is better | Cost efficiency required to meet a budget target. An increase generally indicates stronger performance or control. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | (10−9)/(10−9.6) | 2.5 | 14
KPI-130 | Financial Forecasting | Cost Forecast Accuracy | Measures accuracy of the latest cost forecast. | 1 − [Forecast − Actual] ÷ Actual | Leading | Trigger-based | Planning and execution; especially monthly forecasting and financial governance | Threshold/tolerance: ≥ 90% | What is the latest expected outcome, and is corrective action needed now? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | ≥ 90% | ↑ Higher is better | Measures accuracy of the latest cost forecast. An increase generally indicates stronger performance or control. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | Forecast ₹10.1Cr; actual ₹10Cr | 99% | 14
KPI-131 | Financial Forecasting | Cash Flow Variance | Difference between planned and actual project cash flow. | Planned cash flow − actual cash flow | Lagging / performance | Trigger-based | Planning and execution; especially monthly forecasting and financial governance | Threshold/tolerance: Within tolerance | Is the financial forecasting variance within the approved tolerance, and what corrective action is required? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | Within tolerance | ↔ Closer to 0 / within tolerance is better | Difference between planned and actual project cash flow. The preferred result is to remain close to the approved target or tolerance. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | Plan ₹2.0Cr; actual ₹2.2Cr | −₹0.2Cr | 14
KPI-132 | Financial Forecasting | Funding Utilization % | Percentage of approved funding consumed. | [Funding used ÷ approved funding] × 100 | Leading | Always-on | Planning and execution; especially monthly forecasting and financial governance | Threshold/tolerance: Within approved plan | Do we have the right capacity and allocation to sustain delivery? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | Within approved plan | ↑ Higher is better | Percentage of approved funding consumed. An increase generally indicates stronger performance or control. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | ₹7Cr used / ₹10Cr approved | 70% | 14
KPI-133 | Financial Forecasting | Investment / Project Spend | Total project investment incurred to date. | Σ project expenditure | Lagging / performance | Always-on | Planning and execution; especially monthly forecasting and financial governance | Trigger on material adverse trend, exception, or management concern | What is the expected final financial position and what action is required now? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | Context-dependent | ↔ Context-dependent / target-driven | Total project investment incurred to date. The preferred result is to remain close to the approved target or tolerance. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | Cumulative project spend | ₹7.2Cr | 14
KPI-134 | Financial Forecasting | Financial Risk Exposure | Expected financial exposure from identified project risks. | Σ[Probability × financial impact] | Leading | Trigger-based | Planning and execution; especially monthly forecasting and financial governance | Trigger on material adverse trend, exception, or management concern | What is the expected final financial position and what action is required now? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | Context-dependent | ↓ Lower is better | Expected financial exposure from identified project risks. A decline generally indicates improving control or less exposure. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | Σ probability × impact | ₹1.2Cr | 14
KPI-135 | Financial Forecasting | Contingency Burn Rate | Rate at which contingency is being consumed. | Contingency used ÷ elapsed periods | Leading | Always-on | Planning and execution; especially monthly forecasting and financial governance | Trigger on material adverse trend, exception, or management concern | What is the expected final financial position and what action is required now? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | Context-dependent | ↓ Lower is better | Rate at which contingency is being consumed. A decline generally indicates improving control or less exposure. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | ₹0.5Cr used / 8 months | ₹0.063Cr/mo | 14
KPI-136 | Financial Forecasting | Forecast Variance to Budget | Expected final deviation from approved budget. | EAC − BAC | Leading | Trigger-based | Planning and execution; especially monthly forecasting and financial governance | Threshold/tolerance: ≤ 0 | Is the financial forecasting variance within the approved tolerance, and what corrective action is required? | Project Manager / Finance Business Partner / PMO | ERP / project financials / forecast model / cash-flow tracker | W | ≤ 0 | ↓ Lower is better | Expected final deviation from approved budget. A decline generally indicates improving control or less exposure. | Update forecast, protect funding, control spend, revise contingency, or escalate financial exposure. | EAC ₹10.3Cr; BAC ₹10Cr | +₹0.3Cr | 14
KPI-137 | Governance & Decision Management | Governance Compliance Score | Percentage of required governance controls completed. | [Completed controls ÷ required controls] × 100 | Lagging / outcome | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: ≥ 95% | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | ≥ 95% | ↑ Higher is better | Percentage of required governance controls completed. An increase generally indicates stronger performance or control. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | 190 controls completed / 200 | 95% | 15
KPI-138 | Governance & Decision Management | Steering Committee Effectiveness | Measures quality and effectiveness of steering governance. | Weighted effectiveness score | Lagging / outcome | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: ≥ 80 / 100 | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | ≥ 80 / 100 | ↑ Higher is better | Measures quality and effectiveness of steering governance. An increase generally indicates stronger performance or control. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | Governance pulse | 84/100 | 15
KPI-139 | Governance & Decision Management | Decision Cycle Time | Average time to reach a required project decision. | Σ decision days ÷ decisions made | Leading | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: Lower is better | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | Lower is better | ↓ Lower is better | Average time to reach a required project decision. A decline generally indicates improving control or less exposure. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | 100 days / 20 decisions | 5 days | 15
KPI-140 | Governance & Decision Management | Decision Backlog | Number of pending decisions beyond the agreed due date. | Count of overdue decisions | Leading | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: 0 / minimal | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | 0 / minimal | ↓ Lower is better | Number of pending decisions beyond the agreed due date. A decline generally indicates improving control or less exposure. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | Overdue decisions | 4 | 15
KPI-141 | Governance & Decision Management | Action Item Closure Rate | Percentage of governance actions closed on time. | [Actions closed on time ÷ actions due] × 100 | Lagging / performance | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: ≥ 90% | Are governance & decision management items being resolved/closed fast enough, and where is intervention needed? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | ≥ 90% | ↑ Higher is better | Percentage of governance actions closed on time. An increase generally indicates stronger performance or control. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | 45 closed / 50 due | 90% | 15
KPI-142 | Governance & Decision Management | Audit Findings Count | Number of open audit or assurance findings. | Count of open findings | Lagging / performance | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: 0 critical | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | 0 critical | ↔ Context-dependent / target-driven | Number of open audit or assurance findings. The preferred result is to remain close to the approved target or tolerance. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | Open audit findings | 2 | 15
KPI-143 | Governance & Decision Management | Policy Compliance Rate | Percentage of applicable project policies complied with. | [Compliant items ÷ applicable items] × 100 | Lagging / outcome | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: ≥ 95% | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | ≥ 95% | ↑ Higher is better | Percentage of applicable project policies complied with. An increase generally indicates stronger performance or control. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | 190 compliant / 200 | 95% | 15
KPI-144 | Governance & Decision Management | Change Control Board Efficiency | Percentage of change decisions made within SLA. | [Changes decided within SLA ÷ changes submitted] × 100 | Lagging / performance | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: ≥ 90% | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | ≥ 90% | ↑ Higher is better | Percentage of change decisions made within SLA. An increase generally indicates stronger performance or control. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | 27 within SLA / 30 | 90% | 15
KPI-145 | Governance & Decision Management | Document Approval Rate | Percentage of required project documents approved within SLA. | [Documents approved within SLA ÷ documents due] × 100 | Lagging / performance | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: ≥ 95% | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | ≥ 95% | ↑ Higher is better | Percentage of required project documents approved within SLA. An increase generally indicates stronger performance or control. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | 47 within SLA / 50 | 94% | 15
KPI-146 | Governance & Decision Management | Lessons Learned Implementation % | Percentage of agreed lessons translated into actions. | [Lessons implemented ÷ lessons agreed] × 100 | Lagging / performance | Governance | Governance forums, steering reviews and decision/escalation points | Threshold/tolerance: ≥ 80% | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | ≥ 80% | ↑ Higher is better | Percentage of agreed lessons translated into actions. An increase generally indicates stronger performance or control. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | 16 implemented / 20 | 80% | 15
KPI-147 | Governance & Decision Management | Knowledge Reuse Rate | Percentage of project assets reused from prior approved assets. | [Reused assets ÷ eligible assets] × 100 | Lagging / performance | Governance | Governance forums, steering reviews and decision/escalation points | Trigger on adverse downward trend or missed improvement trajectory | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | Trending up | ↑ Higher / upward trend is better | Percentage of project assets reused from prior approved assets. An increase generally indicates stronger performance or control. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | 18 reused / 24 eligible | 75% | 15
KPI-148 | Governance & Decision Management | Continuous Improvement Index | Composite measure of project process improvement. | Improvement score | Lagging / performance | Governance | Governance forums, steering reviews and decision/escalation points | Trigger on adverse downward trend or missed improvement trajectory | Are governance controls effective and are decisions/actions being closed on time? | Project Sponsor / Steering Committee / PMO | Governance calendar / decision log / action log / audit records | W | Trending up | ↑ Higher / upward trend is better | Composite measure of project process improvement. An increase generally indicates stronger performance or control. | Escalate overdue decisions, reinforce governance controls, assign owners, or convene the appropriate forum. | Composite improvement score | 82/100 | 15
KPI-149 | Lessons Learned & Continuous Improvement | Lessons Logged | Number of lessons captured during the project. | Count of lessons logged | Lagging / performance | Diagnostic | Retrospectives, phase gates and project closure | Trigger on material adverse trend, exception, or management concern | Are lessons being converted into measurable improvement and reusable knowledge? | Project Manager / PMO / Continuous Improvement Lead | Lessons register / retrospectives / improvement backlog / knowledge repository | W | Context-dependent | ↔ Context-dependent / target-driven | Number of lessons captured during the project. The preferred result is to remain close to the approved target or tolerance. | Implement agreed improvements, assign owners, reuse proven assets, or retire ineffective practices. | Lessons captured | 24 | 16
KPI-150 | Lessons Learned & Continuous Improvement | Lessons Implemented | Percentage of agreed lessons acted upon. | [Lessons implemented ÷ lessons logged] × 100 | Lagging / outcome | Diagnostic | Retrospectives, phase gates and project closure | Threshold/tolerance: ≥ 70% | Are lessons being converted into measurable improvement and reusable knowledge? | Project Manager / PMO / Continuous Improvement Lead | Lessons register / retrospectives / improvement backlog / knowledge repository | W | ≥ 70% | ↑ Higher is better | Percentage of agreed lessons acted upon. An increase generally indicates stronger performance or control. | Implement agreed improvements, assign owners, reuse proven assets, or retire ineffective practices. | 18 implemented / 24 | 75% | 16
KPI-151 | Lessons Learned & Continuous Improvement | Lesson Effectiveness | Measures whether implemented lessons produced the intended improvement. | Effectiveness score | Lagging / outcome | Diagnostic | Retrospectives, phase gates and project closure | Threshold/tolerance: ≥ 75 / 100 | Are lessons being converted into measurable improvement and reusable knowledge? | Project Manager / PMO / Continuous Improvement Lead | Lessons register / retrospectives / improvement backlog / knowledge repository | W | ≥ 75 / 100 | ↑ Higher is better | Measures whether implemented lessons produced the intended improvement. An increase generally indicates stronger performance or control. | Implement agreed improvements, assign owners, reuse proven assets, or retire ineffective practices. | Effectiveness pulse | 82/100 | 16
KPI-152 | Lessons Learned & Continuous Improvement | Rework Reduction % | Reduction in rework compared with the prior period or baseline. | [(Prior rework − current rework) ÷ prior rework] × 100 | Lagging / performance | Diagnostic | Retrospectives, phase gates and project closure | Threshold/tolerance: ≥ 20% | Are lessons being converted into measurable improvement and reusable knowledge? | Project Manager / PMO / Continuous Improvement Lead | Lessons register / retrospectives / improvement backlog / knowledge repository | W | ≥ 20% | ↑ Higher is better | Reduction in rework compared with the prior period or baseline. An increase generally indicates stronger performance or control. | Implement agreed improvements, assign owners, reuse proven assets, or retire ineffective practices. | 40 rework hrs / 500 total | 8% | 16
KPI-153 | Lessons Learned & Continuous Improvement | Process Improvement Count | Number of approved process improvements implemented. | Count of improvements implemented | Lagging / performance | Diagnostic | Retrospectives, phase gates and project closure | Trigger on material adverse trend, exception, or management concern | Are lessons being converted into measurable improvement and reusable knowledge? | Project Manager / PMO / Continuous Improvement Lead | Lessons register / retrospectives / improvement backlog / knowledge repository | W | Context-dependent | ↔ Context-dependent / target-driven | Number of approved process improvements implemented. The preferred result is to remain close to the approved target or tolerance. | Implement agreed improvements, assign owners, reuse proven assets, or retire ineffective practices. | Improvements implemented | 12 | 16
KPI-154 | Lessons Learned & Continuous Improvement | Best Practice Adoption % | Percentage of identified applicable best practices adopted. | [Practices adopted ÷ applicable practices] × 100 | Lagging / outcome | Diagnostic | Retrospectives, phase gates and project closure | Threshold/tolerance: ≥ 80% | Are lessons being converted into measurable improvement and reusable knowledge? | Project Manager / PMO / Continuous Improvement Lead | Lessons register / retrospectives / improvement backlog / knowledge repository | W | ≥ 80% | ↑ Higher is better | Percentage of identified applicable best practices adopted. An increase generally indicates stronger performance or control. | Implement agreed improvements, assign owners, reuse proven assets, or retire ineffective practices. | 16 adopted / 20 applicable | 80% | 16
KPI-155 | Lessons Learned & Continuous Improvement | Retrospective Effectiveness | Quality and usefulness of retrospective outcomes. | Retrospective effectiveness score | Lagging / outcome | Diagnostic | Retrospectives, phase gates and project closure | Threshold/tolerance: ≥ 75 / 100 | Are lessons being converted into measurable improvement and reusable knowledge? | Project Manager / PMO / Continuous Improvement Lead | Lessons register / retrospectives / improvement backlog / knowledge repository | W | ≥ 75 / 100 | ↑ Higher is better | Quality and usefulness of retrospective outcomes. An increase generally indicates stronger performance or control. | Implement agreed improvements, assign owners, reuse proven assets, or retire ineffective practices. | Retrospective pulse | 78/100 | 16
KPI-156 | Lessons Learned & Continuous Improvement | Knowledge Asset Creation | Number of reusable project assets created and approved. | Count of knowledge assets | Lagging / outcome | Diagnostic | Retrospectives, phase gates and project closure | Trigger on material adverse trend, exception, or management concern | Are lessons being converted into measurable improvement and reusable knowledge? | Project Manager / PMO / Continuous Improvement Lead | Lessons register / retrospectives / improvement backlog / knowledge repository | W | Context-dependent | ↔ Context-dependent / target-driven | Number of reusable project assets created and approved. The preferred result is to remain close to the approved target or tolerance. | Implement agreed improvements, assign owners, reuse proven assets, or retire ineffective practices. | Reusable assets approved | 15 | 16
KPI-157 | Project Closure & Transition | Closure Plan Compliance | Percentage of closure activities completed as planned. | [Closure activities completed ÷ planned] × 100 | Lagging / outcome | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: ≥ 95% | Is the project ready to hand over, close and sustain the intended outcome? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | ≥ 95% | ↑ Higher is better | Percentage of closure activities completed as planned. An increase generally indicates stronger performance or control. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | 95 closure tasks / 100 | 95% | 17
KPI-158 | Project Closure & Transition | Deliverable Handover % | Percentage of required deliverables formally handed over. | [Deliverables handed over ÷ total deliverables] × 100 | Lagging / outcome | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: ≥ 95% | Is the project ready to hand over, close and sustain the intended outcome? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | ≥ 95% | ↑ Higher is better | Percentage of required deliverables formally handed over. An increase generally indicates stronger performance or control. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | 47 handed over / 50 | 94% | 17
KPI-159 | Project Closure & Transition | Operational Acceptance Rate | Percentage of deliverables formally accepted by the receiving function. | [Accepted deliverables ÷ handed-over deliverables] × 100 | Lagging / outcome | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: ≥ 95% | Is the project ready to hand over, close and sustain the intended outcome? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | ≥ 95% | ↑ Higher is better | Percentage of deliverables formally accepted by the receiving function. An increase generally indicates stronger performance or control. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | 47 accepted / 50 | 94% | 17
KPI-160 | Project Closure & Transition | Transition Readiness Score | Measures readiness of receiving teams to take ownership. | Transition readiness score | Lagging / outcome | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: ≥ 85 / 100 | Is the project ready to hand over, close and sustain the intended outcome? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | ≥ 85 / 100 | ↑ Higher is better | Measures readiness of receiving teams to take ownership. An increase generally indicates stronger performance or control. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | Readiness assessment | 88/100 | 17
KPI-161 | Project Closure & Transition | Warranty Defect Rate | Defects raised during the warranty period relative to delivered items. | [Warranty defects ÷ delivered items] × 100 | Lagging / performance | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: ≤ agreed threshold | Is quality within the acceptance threshold for the current delivery gate? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | ≤ agreed threshold | ↓ Lower is better | Defects raised during the warranty period relative to delivered items. A decline generally indicates improving control or less exposure. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | 4 defects / 100 deliverables | 4% | 17
KPI-162 | Project Closure & Transition | Documentation Completeness | Percentage of required project documentation completed and approved. | [Completed documents ÷ required documents] × 100 | Lagging / outcome | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: ≥ 95% | Is the project ready to hand over, close and sustain the intended outcome? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | ≥ 95% | ↑ Higher is better | Percentage of required project documentation completed and approved. An increase generally indicates stronger performance or control. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | 190 complete / 200 | 95% | 17
KPI-163 | Project Closure & Transition | Post-Implementation Review Completion | Whether the formal post-implementation review was completed. | [Completed PIR ÷ planned PIR] × 100 | Lagging / outcome | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: 100% | Is the project ready to hand over, close and sustain the intended outcome? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | 100% | ↑ Higher is better | Whether the formal post-implementation review was completed. An increase generally indicates stronger performance or control. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | PIR completed | 100% | 17
KPI-164 | Project Closure & Transition | Benefits Handover | Confirms agreed ownership of post-project benefit tracking. | [Benefits ownership confirmed ÷ required ownership] × 100 | Lagging / outcome | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: 100% | Is the project ready to hand over, close and sustain the intended outcome? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | 100% | ↔ Context-dependent / target-driven | Confirms agreed ownership of post-project benefit tracking. The preferred result is to remain close to the approved target or tolerance. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | Benefits owners confirmed | 100% | 17
KPI-165 | Project Closure & Transition | Contract Closure Timeliness | Percentage of project contracts closed within the agreed timeline. | [Contracts closed on time ÷ contracts due] × 100 | Lagging / performance | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: ≥ 95% | Is the project ready to hand over, close and sustain the intended outcome? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | ≥ 95% | ↑ Higher is better | Percentage of project contracts closed within the agreed timeline. An increase generally indicates stronger performance or control. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | 9 closed on time / 10 | 90% | 17
KPI-166 | Project Closure & Transition | Archival Compliance | Percentage of required project records archived correctly. | [Archived compliant records ÷ required records] × 100 | Lagging / outcome | Phase-specific | Hypercare, transition and formal project closure | Threshold/tolerance: ≥ 95% | Is the project ready to hand over, close and sustain the intended outcome? | Project Manager / Transition Lead / Business Owner | Closure checklist / handover pack / acceptance records / PIR / archive | W | ≥ 95% | ↑ Higher is better | Percentage of required project records archived correctly. An increase generally indicates stronger performance or control. | Close outstanding gaps, complete handover, confirm ownership, resolve warranty defects, or delay closure until criteria are met. | 190 compliant / 200 records | 95% | 17

## Field Standard
Field | Definition / Use
KPI | Name and unambiguous definition
Formula / Calculation | Calculation logic and units
Nature | Leading / lagging / outcome
Activation | Always-on / phase / trigger / diagnostic / governance
When to Use | Lifecycle stage or management situation
Trigger | Threshold, event or condition
Decision | Question the KPI should answer
Owner | Accountable role
Data Source | System / report / evidence
Cadence | Daily / weekly / monthly / event-based
Target / Tolerance | Expected level and escalation band
Action | Intervention if KPI deteriorates
Direction of Improvement | Shows whether movement up/down generally indicates better performance; uses source target language where available.
What the KPI Indicates | Short management interpretation of what the KPI is telling the project team.